## Sheet1
Test Suite: GT New Unit FPY - Alpha SW
Test Case | Description | Expected Results
Prerequisites | Items that must be complete prior to Alpha software | 1. 6 weeks after CKOM verify VM exists (attach link to request). - If Equipment Only request VM with separate CMS server - If Extended Scope verify VM exists, if not reach out to plant lead for VM status 2. Generate Software and roll into CMS server on VM(no SW development should occur outside of CSM) 3. A210FIO Complete and accurate including and IO related A210 issues 4. Latest HMI screens available
Attributes Review | Review attributes with SME, PO or Architect or CTH | Pass - All Attributes are set correctly based on contractual requirement Conditioning Pass - All Critical Attributes are set correctly Fail - Any Critical Attributes are not set correctly
Alpha Code Library Update | Update Libraries to latest release | Pass - Update to latest approved libraries release for frame size specific Fail - Not utilizing latest approved libraries release for frame size specific
Remove Simulation Code | All VARSIM and simulation code should be removed from GT controller | 1. Remove Program "SimulationGasTurbine" 2. No VARSIM blocks exist in controller
Coding Practices | Complete coding practices | Pass - Review coding practice reports and clear all possible items. If any items require custom code, define all necessary IO and variables. Fail - External constants not in Neptune
Neptune Constants Complete | Complete Neptune calculated constants and import into controller | Pass - All Neptune calculated constant parameters are filled and imported constants into controller Fail - Critical calculated constants parameters are not filled. Ex: Gas fuel composition Conditional Pass - All Critical calculated constants parameters are filled and imported into controller
A210PC Constants Complete | Imported A210PC constants into controller | Pass - Utilizing MBC tools to generate A210PC constants and imported into controller. Fail - If A210PC constants have not been generated and imported into controller
A210CBM Constants Complete | A210CBM Constants Applied to Project | Pass - Imported A210CBM constants into controllers Conditioning Passed - If A210CBM not available, then reach out to standard team to confirm B03 is maintained for all frames in Neptune. Fail: A210CBM not available an B03 is not maintained in Neptune
Add external constants to Neptune | Add external constants to Neptune | Pass - Added A210PC, A210CBM, A210GRID, Hot lists constants, A210CGE to external constants in Neptune Fail: Not done yet.
Digital IO Config | Review Digital Configs | Pass - All of the following are true: 1. Sequence of Events enabled on all used digital inputs and outputs 2. Any unused contacts set to Unused 3. On TDBT boards all Solenoids are landed on Relays 1 - 6 4. Review IOs to ensure no single point failure (TMR IOs fanned out correctly) Failed - If any of the conditions above is not true
Analog IO Config | Review Analog Cards and confirm settings | Pass - All of the following are true: 1. All ranges set per 0414 (Device Summary) 2. PAIC-* -> Parameters CompressorStallType = Unused 3. Input Filter = 12Hz 4. DiagHighEnable = True 5. DiagLowEnab = True 6. Any unused IO points set to Unused Failed - If any of the conditions above is not true
Barcode Import | Import Barcodes using process defined in Confluence. https://engineeringconfluence.pw.ge.com/pages/releaseview.action?pageId=67077210 | Alpha: Barcodes imported into controllers.
Review SIL alpha check list | Review SIL alpha checklist in confluence https://engineeringconfluence.pw.ge.com/pages/releaseview.action?pageId=988775818 | Pass - Complete SIL alpha check list and GT SIL alpha CLM milestone approved by SIL team Fail - Not done yet
Audit controllers, EGD devices , and externa devices IP address based on 4108 drawing | Audit controllers (GT, GT1), EGD devices (G60s,T60U/T, etc.), externa devices (E1 and L1) IP address based on 4108 drawing | Pass - All controllers, EGD device, and external devices IP addresses matched 4108 drawing Fail - Not done yet
Audit GT1 and GT1S controllers name based on 4108 drawing | Audit GT1 and GT1S controllers name based on 4108 drawing | Pass - All GT controllers name must matched 4108 drawing Fail - Not done yet